## Mental Health
Goal | Objective | Strategy | Lead Organization | Indicator | Aim | Oct-Dec 2022 Progress/Results | Jan-Mar 2023 Progress/Results | Apr-Jun 2023 Progress/Results | Jul-Sept 2023 Progress/Results | Oct-Dec 2023 Progress/Results | Jan-Mar 2024 Progress/Results | Apr-Jun 2024 Progress/Results | Jul-Sept 2024 Progress/Results | Oct-Dec 2024 Progress/Results | Jan-Mar 2025 Progress/Results | Apr-Jun 2025 Progress/Results
Goal 1: To enhance collaboration among traditional and non-traditional partners to address mental health. | Objective 1: Provide students and staff with resources that facilitate awareness about behavioral health that align with each school and/or division's suicide prevention plans by June 30, 2025. | Strategy 1: Mental Health America of Fredericksburg (MHAfred) will present Signs of Suicide (SOS), an evidence-based suicide prevention education program for middle schoolers and high schoolers, at each school district within PD16 that partners with MHAfred through June 30, 2025. During this same timeframe, MHAfred will also present SOS to other entities such as youth groups, private schools, several homeschools, juvenile detention centers, and underserved communities. Where SOS has been presented, MHAfred will partner with other organizations to support student or youth led clubs that promote mental wellness. | MHAfred | Number of SOS presentations each year, including date, location, and number of students in attendance | ????
|  |  |  | Information about partnerships MHAfred has built with other organizations to support student or youth led clubs that promote mental wellness | n/a
|  | Strategy 2: Rappahannock Area Community Services Board (RACSB) will provide Mental Health First Aid training to a minimum of 10% of personnel in each interested school within PD16 by June 30, 2025. | RACSB | Number of Mental Health First Aid trainings presented each quarter, including date, location, and number of school personnel in attendance | 3 trainings per quarter
|  | Strategy 3: By June 30, 2025, RACSB and MHAfred will coordinate the implementation of teen Mental Health First Aid within one high school in PD16 where the criteria set forth by Mental Health First Aid USA is met. Additionally, another high school or school division will be in the implementation process by June 30, 2025. | RACSB | Date teen MHFA training is implemented, including information about what school it was presented at and how many students were in attendance | By June 30, 2025
|  |  |  | Information about continuing efforts to implement the training at another high school or school division | n/a
|  | Strategy 4: Through March 14, 2023, RACSB will pilot the provision of behavioral health services through the Children and Adolescent Behavioral Health Pandemic Supports program to over 100 children in a PD16 school district. The focus will be on children who currently do not receive these services through other mechanisms. | RACSB | Number of unique students participating in the Children and Adolescent Behavioral Health Pandemic Supports program each quarter | 34 per quarter
|  |  |  | Information about how the program is going, including any modifications that have been made | n/a
|  | Strategy 5: By June 30, 2023, RACSB will evaluate results from the Children and Adolescent Behavioral Health Pandemic Supports program pilot and modify the program as needed. Results will be communicated to other PD16 school districts looking for expansion opportunities. | RACSB | Date results are evaluated and shared with other PD16 school districts | By June 30, 2023
|  |  |  | Information about the evaluation results, including next steps if applicable and potential expansion to other PD16 school districts | n/a
Goal 2: To improve access to behavioral health services, including prevention, treatment, and recovery. | Objective 1: Expand access to and awareness of telehealth behavioral health services in at least one rural community within PD16 by March 31, 2023. | Strategy 1: Starting July 1, 2022 and ending March 31, 2023, MHAfred will work with Caroline County stakeholders to evaluate strategies for overcoming barriers to accessing telehealth mental health services for residents without internet and with limited transportation options. The evaluation results will determine additional strategies. | MHAfred | List of Caroline County stakeholders MHAfred worked with to evaluate strategies for overcoming barriers to accessing telehealth mental health services | n/a
|  |  |  | Date evaluation is complete | By March 31, 2023
|  |  |  | Information about what the evaluation showed, including next steps and possibly adding additional strategies to the CHIP | n/a
| Objective 2: Increase normalization of, and education about, currently available mental health resources, especially to underserved populations by June 30, 2025. | Strategy 1: Through June 30, 2025, RACSB and MHAfred will partner to promote existing services, such as counseling, emergency services, telehealth, grief counseling, support groups, and new 988 services through social media, websites, community partners, and tabling events, in English and at least one additional language. | RACSB | Quarterly updates about promotion initiatives, including dates, modality used, location, service promoted, language(s) used, and target population | n/a
|  | Strategy 2: Through June 30, 2025, RACSB will continue to promote and host evidenced-based curriculums including but not limited to: ACE Interface; Mental Health First Aid; safeTALK; Applied Suicide Intervention Skills Training (ASIST); and REVIVE! to stakeholders and interested community members (including African-American, Asian, disabled, Latinx, and LGBTQIA+ communities). | RACSB | Number of curriculums hosted each quarter, including name of the program, location, date, target population, and number of attendees | 3 ACE Interface trainings per quarter 3 Mental Health First Aid trainings per quarter 1 safeTALK training per quarter 0-1 Applied Suicide Intervention Skills training per quarter 6 REVIVE! trainings per quarter
|  | Strategy 3: Starting July 1, 2022 to June 30, 2025 MHAfred and RAHD will partner to market the HELPLINE using print media, social media, and outreach to underserved population groups and primary care physicians. MHAfred will increase the number of HELPLINE follow-ups per year from 1,200 to 10,000. | MHAfred | Quarterly updates about marketing initiatives, including dates, modality used, location(s), and target population. | n/a
|  |  |  | Number of HELPLINE follow-ups each quarter | 2,500 per quarter
| Objective 3: Increase the number of available licensed mental health providers in the PD16 area by December 31, 2023. | Strategy 1: The Fredericksburg Christian Health Center (FCHC) will obtain grants and local funding/donations in the amount of $95,000 in order to employ a full time Licensed Professional Counselor by February 2023. | FCHC | Information about obtained funding, including amount and source | n/a
|  |  |  | Information about hired full time counselor, including name, educational background, and how to schedule an appointment with them | n/a
|  |  |  | Date full time counselor is hired | By March 2023
|  | Strategy 2: FCHC’s counselor will provide behavioral health services to FCHC clients, with the aim of providing at least 600 counseling sessions to 100 clients through December 31, 2023 (and eventually up to 1200 sessions/year once the position is fully established.) The result of these sessions will be reduced PHQ-9 and Zung Anxiety Index Scores, from first counseling session to the last session. | FCHC | Number of counseling sessions performed each quarter, starting in Q2 | 200 counseling sessions per quarter | n/a
|  |  |  | Number of clients seen each quarter | 35 clients seen per quarter | n/a
|  |  |  | Average percent reduction in PHQ-9 and Zung Anxiety Index Score for clients seen by the counselor | 5-point reduction in PHQ-9 Score or 25% reduction in Zung Anxiety Index Score | n/a

## Affordable Housing
Goal | Objective | Strategy | Lead Organization | Indicator | Aim | Oct-Dec 2022 Progress/Results | Jan-Mar 2023 Progress/Results | Apr-Jun 2023 Progress/Results | Jul-Sept 2023 Progress/Results | Oct-Dec 2023 Progress/Results | Jan-Mar 2024 Progress/Results | Apr-Jun 2024 Progress/Results | Jul-Sept 2024 Progress/Results | Oct-Dec 2024 Progress/Results | Jan-Mar 2025 Progress/Results | Apr-Jun 2025 Progress/Results
Goal 1: To develop and promote policies that ensure equitable housing opportunities for all. | Objective 1: Form a diverse group of advocates to address the issue of Affordable Housing in PD16 by December 31, 2022. | Strategy 1: By July 1, 2022, George Washington Regional Commission (GWRC) will identify members of the community with a vested interest in the issue of affordable housing to participate in the group. | GWRC | Number of community members invited to join the group | ???
|  |  |  | Number of participants in the group | ???
|  |  |  | Information about how members were identified and invited | n/a
|  | Strategy 2: GWRC will create a framework document, which will include assigning roles and responsibilities and identifying top priorities of the group, by December 31, 2022. | GWRC | Date framework document is completed | By December 31, 2022
|  |  |  | Information about the document including top priorities of the group | n/a
| Objective 2: Develop and implement strategies to address top priorities of the group by June 30, 2025. | Strategy 1: Develop strategies to address top priorities of the group by December 31, 2023. | GWRC | Date strategies are developed | By December 31, 2023
|  |  |  | Information about the strategies, including how these strategies were developed/steps taken | n/a
|  | Strategy 2: Have at least 1 meeting with each local government, including rural localities, to discuss the identified priorities of the group by June 30, 2025. | GWRC | Date of meetings with each locality | Each by June 30, 2025
|  |  |  | Information about what was discussed in these meetings, meeting minutes, which stakeholders and policymakers attended, and any decisions made | n/a
|  | Strategy 3: Meet with state representatives to discuss the identified priorities of the group by June 30, 2025. | GWRC | Date of meeting with state representative | By June 30, 2025
|  |  |  | Information about what was discussed in the meeting, meeting minutes, who attended, and any decisions made | n/a
Goal 2: Increase the number of safe, sustainable communities with affordable housing options throughout PD16. | Objective 1: By June 30, 2025, increase the number of new homes built in PD16 for underserved populations. | Strategy 1: A collaborative, compromised of Micah Ecumenical Ministries, Virginia Supportive Housing, Mary Washington Healthcare, and the City of Fredericksburg, will evaluate potential housing sites and recruit partners for a multi-faceted housing development for the street and chronic homeless population. Site control and zoning permission will be in place by March 2023. The development will include 60-80 multifamily units developed by Virginia Supportive Housing and 30-50 small, single-family detached or duplex homes known as the Jeremiah Community, which will be developed by Micah Ecumenical Ministries. | Micah Ecumenical Ministries | Date site control and zoning permission are in place | By March 2023 | See update below.
|  |  |  | Quarterly updates about the progress towards building 60-80 multifamily units and 30-50 single-family or duplex homes | n/a | Micah and Virginia Supportive Housing met with the City of Fredericksburg to discuss necessary steps to rezone a parcel of land for Jeremiah Community. There are necessary changes that must be made to the city zoning ordinance. Proposed changes will be considered by city council in early October. We can file for a rezoning once that conversation is under way. Micah's board of directors has been researching successful Capital campaigns. We will meet this month to put together a campaign committee to begin engaging people in fundraising.
|  |  |  | List of partners | n/a | No results at this time.
|  | Strategy 2: The collaborative will obtain necessary resources and approvals for site development for construction to begin by Spring 2024. | Micah Ecumenical Ministries | Date resources and approvals for site development are obtained | By Spring 2024
|  |  |  | Quarterly updates about the progress towards obtaining resources and approvals, including details about specific resources and sources | n/a
|  | Strategy 3: The collaborative will develop a robust network of support services targeted for the people moving into the housing development by June 20, 2025. | Micah Ecumenical Ministries | List of support services or organizations in the network | n/a
|  |  |  | Quarterly updates about the progress towards building a network of support services, including information about what organizations have joined the network and what services they provide | n/a

## Access to Healthcare
Goal | Objective | Strategy | Lead Organization | Indicator | Aim | Oct-Dec 2022 Progress/Results | Jan-Mar 2023 Progress/Results | Apr-Jun 2023 Progress/Results | Jul-Sept 2023 Progress/Results | Oct-Dec 2023 Progress/Results | Jan-Mar 2024 Progress/Results | Apr-Jun 2024 Progress/Results | Jul-Sept 2024 Progress/Results | Oct-Dec 2024 Progress/Results | Jan-Mar 2025 Progress/Results | Apr-Jun 2025 Progress/Results
Goal 1: To improve access and collaboration for preventative services for all members of the community. | Objective 1: Expand Diabetes Prevention and Blood Pressure Self-Monitoring programs into the community by leveraging collaborations with traditional and non-traditional partners, focusing on population groups with existing disparities (eg. African Americans, Hispanics, Native Americans, Seniors, low income) by June 30, 2025. | Strategy 1: The Rappahannock Area Young Men’s Christian Association (YMCA) will join the Unite Us network of community providers to streamline the referral process for the Diabetes Prevention and Blood Pressure Self-Monitoring programs by December 31, 2022. | Rappahannock Area YMCA | Date Diabetes Prevention program is added to the Unite Us platform | By December 31, 2022 | The Rappahannock Area Young Men’s Christian Association (YMCA) is pleased to announce that we have registered with Unite Us and listed all of our Community Health and therapeutic programs on the platform. We have since received our first referral. We plan to train staff at each of our branches to provide and receive referrals.
|  |  |  | Date Blood Pressure Self-Monitoring program is added to the Unite Us platform | By December 31, 2022
|  |  |  | Date first referral for the Diabetes Prevention program is received | By December 31, 2022
|  |  |  | Date first referral for the Blood Pressure Self-Monitoring program is received | By December 31, 2022
|  | Strategy 2: The Rappahannock Area YMCA, MWHC, and other organizations will educate and provide program awareness to healthcare providers, Care Coordinators, Community Health Workers, and community leaders by providing periodic presentations starting by November 30, 2022 and continuing on a quarterly basis. | Rappahannock Area YMCA | Number of presentations hosted each quarter including information about the location, date, time, and target population | 1 per quarter | On Monday, October 10th, 2022, the Rappahannock Area YMCA held a partnership meeting with the Fredericksburg Regional Food Bank. Jillian Holmes learned about their strategic plan and efforts to provide health-based nutrition and education. The YMCA plans to partner with the Fredericksburg Regional Food Bank to meet the nutritional needs of people in their chronic disease prevention programs. The YMCA has identified that the Diabetes Prevention Program and Blood Pressure Self Program has necessary food recommendations that may have an access barrier. The Fredericksburg Regional Food Bank has agreed to pilot an effort to support the YMCA's Diabetes Prevention Program (DPP) which is currently being held at the Lloyd Moss Free Clinic. Jillian has provided the Fredericksburg Regional Food Bank with the nutritional suggestions referenced in the CDC's Prevent T2 curriculum. The Fredericksburg Regional Food Bank is in the process of creating an online ordering system similar to their Order Ahead program. The menu will only contain the foods recommended to prevent type 2 diabetes. The Fredericksburg Regional Food Bank will deliver those foods to the participants at their scheduled DPP course. Additionally, the YMCA has an interest in addressing diabetes and hypertension in Caroline County. Jillian has recently identified a Community Health liaison within the YMCA to provide outreach efforts/ interest meetings to local health practitioners and community organizations. They had their first strategy meeting, and plan to offer 4 local churches and one community health clinic an opportunity to learn about Diabetes Prevention Program and Blood Pressure Self-Monitoring Program.
|  |  |  | Number of attendees for each presentation including information on the organization they work for and their position | ???
|  | Strategy 3: The Rappahannock Area YMCA, MWHC, and other organizations will train one additional facilitator per locality, including correctional staff, to support the Diabetes Prevention and Blood Pressure Self-Monitoring programs by June 30, 2025. | Rappahannock Area YMCA | Number of additional facilitators trained each quarter including what locality they’ll work in, organization they work for, their position, and what potential population group/ what specific population they might reach | 2 facilitators per year | The Virginia Center for Diabetes Prevention is hosting a Lifestyle Coach Training in November. The YMCA has one participant scheduled to take that training to prepare to facilitate the Diabetes Prevention Program.
| Objective 2: Provide opportunities for patients throughout PD16 to improve their health literacy by June 30, 2025. | Strategy 1: RAHD will train two RAHD staff and two Healthy Generations staff to be trainers of the Health Education and Literacy (HEAL) program by September 30, 2022. | RAHD | Number of staff trained including what organization they work for and their position | 4 trainers before September 30, 2022 | Keilah Martinez CHW and Ben Henderson completed all training and courses pertaining to the HEAL program. Keilah is looking to train another RAHD employee as Ben Henderson is no longer with RAHD. Two Healthy Generations staff were also trained in the HEAL program.
|  | Strategy 2: By December 31, 2022, RAHD will create a training schedule to improve health literacy by working with organizations that serve the elderly, lower income neighborhoods, Spanish speaking communities, and the incarcerated and recently released population, while expanding the training to other populations impacted by health disparities and inequities. | RAHD | Date training schedule is completed | By December 31, 2022 | Not complete at this time
|  |  |  | List of organizations worked with to complete the training schedule | n/a | None at this time
|  |  |  | Details about which populations the training will be expanded to including what organizations RAHD will work with | n/a | Keilah is now in the recruitment stages of the program. Recruitment to find classes and targeted popultation. The current targeted population is the senior community.
|  | Strategy 3: From January 1, 2023 through June 30, 2025, RAHD will host at least four HEAL trainings per quarter at public libraries and other community locations throughout PD16, including rural and underserved communities. | RAHD | Number of completed trainings | 4 trainings per quarter | No results at this time
|  |  |  | Number of attendees at each training | 5 attendees per training | No results at this time
|  |  |  | Information about how the training went, including details about target population(s), health equity component, location, date, and time | n/a | No results at this time
| Objective 3: Increase utilization of the Unite US platform in PD16 from 90 programs by 25% (approx. 23 programs) related to top three identified CHIP priorities (mental health, affordable housing, and access to healthcare) in PD16 by June 30, 2025. | Strategy 1: MWHC and RAHD will increase awareness of the Unite US user group by providing quarterly educational sessions to 60% of active Unite Us users starting January 2023 to improve equitable access to services through June 30, 2025. | MWHC | Number of educational sessions hosted each quarter | 1 per quarter | 0. This strategy is in the "pre-work" stage. Aim is to schedule quarterly PD 16 user meetings: to review referral data (super users), review new or underutilized platform features/dashboards, spotlight organizations or new organizations on platform, landscape of PD16 (what is happening?) Success/Challenges, and next steps. Educational user group meetings will begin in January 2023, dates will be finalized by the end of October.
|  |  |  | Percent of active Unite Us users attending each session, including their organization and position | 60% | 0
|  | Strategy 2: MWHC and RAHD will work with providers to increase the number of referred cases for the Unite Us platform specific to mental health, affordable housing, and access to healthcare in PD16 from 151 by 20% (approximately 30 referred cases) each year through June 30, 2025. | MWHC | Number of referred cases each quarter, including information on if they were related to mental health, affordable housing, or access to healthcare | 8 per quarter | Waiting for results from Unite Us
| Objective 4: Through June 30, 2025 train residents of PD16 how to use the regional transit system so transportation to healthcare appointments is more achievable. | Strategy 1: Through June 30, 2025, Healthy Generations will use their Transit Travel Training program to train 50 residents of PD16 per year, especially the elderly and disabled, how to utilize FXBGO! Fredericksburg Regional Transit. | Healthy Generations | Number of residents trained each quarter | 13 per quarter | 15
|  |  |  | Information about the trainings including location, date, and number of attendees | n/a | Travel Training was provided to post-graduate students from Colonial Forge High School. The students are young adults with disabilities and they were excited to learn more about how they can travel independently within their community. Includes app tutorials, classroom training, and physical training
|  | Strategy 2: Through June 30, 2025, Healthy Generations will train 36 members of the public per year how to use FXBGO! Fredericksburg Regional Transit to ensure that they can then train others. | Healthy Generations | Number of members of public trained each quarter | 9 per quarter | None at this time
|  |  |  | Information about the trainings including location, date, and number of attendees | n/a | We are working to develop a curriculum for this strategy that is in line with Easterseals Project Action Consulting's Certified Travel Trainer Instruction Program. Once the curriculum is developed we will begin outreach to targeted members of the community who could benefit.
| Objective 5: Provide support to HIV positive residents and continue to work on HIV prevention initiatives through June 30, 2023. | Strategy 1: From July 1, 2022 to December 31, 2022, through “COVID Safe Outreach and Testing Events” Fredericksburg Area Health and Support Services (FAHASS) will provide HIV testing to 100 people from remote, low-income communities, and screen, refer, and connect 25 people to other services they may need, including mental health, housing, and the insurance marketplace. | FAHASS | Number of people provided with HIV testing and demographic details including age, gender, race, ethnicity, and income | 50 per quarter | 30
|  |  |  | Number of people connected to other services and demographic details including age, gender, race, ethnicity, and income | 13 per quarter | 18
|  |  |  | Information about the COVID Safe Outreach and Testing Events including number of attendees, other organizations present, locations, dates, and any other characteristics of the population(s) reached | n/a | In the first quarter, FAHASS was able to test 30 people through “COVID Safe Outreach and Testing Events”, in this measure the counties of Culpeper and Orange were included. They are working in getting into Caroline County, Fauquier County, and other areas where services are needed. FAHASS was able to refer 18 people for additional services. It's been difficult finding resources in the service areas FAHASS is trying to reach. FAHASS will be working in reaching out to more community partners to expand their community resource list in the counties of Culpeper and Orange.
|  | Strategy 2: FAHASS will work with Mosaic Care Center to enroll 20 new people in the PrEP program, which includes monitoring and targeted PrEP treatment from January 1, 2023 to December 31, 2023. | FAHASS | Number of new people enrolled in the PrEP program and demographic details including age, gender, race, ethnicity, and income | 5 people per quarter | FAHASS was able to refer 5 people for PrEP. This quarter they have had some set backs with their PrEP program, since they lost a provider at the Mosaic Care Center, but they are working find a provider that will assist people who are interested in taking PrEP.
|  | Strategy 3: Starting July 1, 2022 until June 30, 2023, FAHASS will continue to expand Medical and Non-Medical Case Management to HIV+ individuals, ensuring that they are in care and improving the viral suppression rate of the agency from 94% to 96%. FAHASS will also work with Mosaic Care Center to access people living in remote areas via telemedicine. | FAHASS | Information about efforts/actions to expand case management to HIV+ individuals | n/a | This quarter FAHASS's Viral Suppression rate was at 94%. They are working with a cohort list of clients who are not yet virally suppressed and/or out of care to get them the resources needed to reach viral suppression.
|  |  |  | Information about efforts/actions to access people living in remote areas with telemedicine | n/a | None reported
|  |  |  | Viral suppression rate of the agency | 96% | 94%
| Objective 6: Create a collaboration of different healthcare service providers to assess healthcare services in PD16 and improve access to healthcare services by April 2023 | Strategy 1: RAHD will invite individual representatives from different healthcare agencies to participate in the collaboration by August 2022. | RAHD | List of invited representatives | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Meeting minutes, including participant list | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Information about efforts/actions collaboration has taken or plans to take | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  | Strategy 2: RAHD, with input from the collaboration, will collect quantitative data from the general public through a survey, and conduct at least two focus group discussions and three key informant interviews by December 2022. | RAHD | Survey | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Focus group facilitator guide | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Informant interview facilitator guide | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Number of informant interviews | 3 | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Date of completion | By December 2022 | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Information about progress/results of data collection | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  | Strategy 3: RAHD will analyze the data to draw conclusions and, with the collaboration, create strategies to address identified challenges by December 2022. | RAHD | Analysis of data, including conclusions | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Strategies to address identified challenges | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Date of completion | By December 2022 | n/a since strategy won't be added to CHIP until after this reporting period
|  | Strategy 4: RAHD and the collaboration will begin implementation and evaluation of the strategies to improve access to healthcare services by April 2023, and have it completed by June 2023. | RAHD | List of strategies marked for implementation | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Implementation plans for each strategy | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Evaluation of strategy implementation | n/a | n/a since strategy won't be added to CHIP until after this reporting period
|  |  |  | Date of completion | By April 2023 | n/a since strategy won't be added to CHIP until after this reporting period
Goal 2: To support the development of a comprehensive strategy and pipeline to increase the healthcare workforce. | Objective 1: Create a new Patient Care Technician (PCT) position that would allow students to acquire both Certified Nurse Aide (CNA) and Clinical Medical Assistant (CMA) certifications in 12 weeks and sit for a single certification by January 31, 2024. | Strategy 1: Germanna Community College (GCC) will secure funding for PCT instruction and student support by June 30, 2023. | GCC | Information about the funding secured for PCT instruction and student support, including amount and funding source | n/a | Go VA grant awarded and executed
|  |  |  | Date funding is secured | By June 30, 2023 | 2022-08-19
|  | Strategy 2: GCC will develop PCT curriculum, which will include health equity and cultural humility training, by June 30, 2023. | GCC | Information about the development of the PCT curriculum, including details about the health equity and cultural humility training | n/a | Progress being made in curriculum development and supplies acquisition for January 2023 launch.
|  |  |  | Date the PCT curriculum is completed | By June 30, 2023 | Not complete at this time.
|  | Strategy 3: GCC will implement PCT program by January 31, 2024. | GCC | Information about the plans to implement the PCT program, including marketing and recruitment of students | n/a | No progress/results to report at this time.
|  |  |  | Date the first class will begin for the PCT program | By January 31, 2024 | No progress/results to report at this time.
| Objective 2: Expand Dual Enrollment offering for CNA and RMA programs within high schools throughout the service area by June 30, 2025. | Strategy 1: GCC will increase the number of dual enrolled students in area high schools, which will include those in rural and underserved areas, by establishing two additional Nurse Assistant/Medication Aide programs within the college service by January 31, 2025. | GCC | Number of dual enrolled students and which high school they attend | ??? | Spotsylvania Career and Technical Center with an additional 31 student enrolled.
|  |  |  | Percent increase in number of dual enrolled students | ??? | From 12 students to 31 = 158% increase
|  |  |  | Information about the two additional Nurse Assistant/Medication Aide programs including location, dates, class size, etc. | n/a | One additional DE HS brought on board in Fall 2022- Spotsylvania Career and Technical Center with an additional 31 student enrolled.
|  | Strategy 2: GCC and other philanthropic organizations will assist with a minimum of $50,000 in student fees through grants and scholarships (with at least 5% of students being minorities or from underserved areas) through June 30, 2025. | GCC | Amount given through grants and scholarships each quarter | $4,200 per quarter | Pending information from the foundation
|  |  |  | Number of students receiving grants and scholarships and if they belong to a minority or are from an underserved area | 5% of students being minorities or from an underserved area | Pending information from the foundation
|  |  |  | Information about what other philanthropic organizations are assisting with grants and scholarships | n/a | Pending information from the foundation
|  | Strategy 3: GCC will help develop a minimum of seven hiring contracts between students and clinical agencies through June 30, 2025. When possible, these contracts will be associated with tuition payment in exchange for a designated amount of service at the facility. At least one contract will be for a minority or disabled student. | GCC | Number of hiring contracts developed between students and clinical agencies, including if the student is a minority or disabled and what agencies the contracts are with | 1 per quarter, with at least one awarded to a minority or disabled student
| Objective 3: Build a career ladder for mental health providers by June 30, 2024. | Strategy 1: GCC, in partnership with RACSB, will develop a career plan for mental health jobs with course offerings, training, certifications, and degree programs by GCC, professional organizations, and local organizations, including health equity and cultural humility training, by June 30, 2023. | GCC | Date the career plan is completed | By June 30, 2023 | Not complete at this time.
|  |  |  | Information about the development of a career plan for mental health jobs, including details about the health equity and cultural humility training piece | n/a | Summit of interested individuals called in August. Curriculum Development sub-group to meet In October 2022 to develop entry level course for Behavioral Health Technicians. Appropriate clinical internships will be aligned as this curriculum is developed.
|  | Strategy 2: GCC, in partnership with RACSB, will secure any necessary approvals and funding for the courses, certifications, and degree programs by December 21, 2023. | GCC | Date funding is secured | By December 21, 2023 | Grant agreement being executed
|  |  |  | Information about the funding secured for mental health career plan including amount and funding source | n/a | Claude Moore Grant $100,000 to GCC funding faculty position
|  | Strategy 3: GCC, in partnership with RACSB, will begin offering courses leading to mental health certifications, licensing, and/or degrees by June 30, 2024, ensuring these programs will be available to those in underserved areas. | GCC | Date mental health courses begin being offered | By June 30, 2024 | Not complete at this time.
|  |  |  | Information about courses being offered including dates, locations, class size, and efforts to make them available in underserved areas | n/a | Curriculum development meeting 10/14/2022. Information being developed in Curriculum sub-group.
| Objective 4: Expand Germanna Community College nursing program to graduate 220 registered nursing candidates per year by June 30, 2025. | Strategy 1: GCC will expand the current nursing facilities by December 31, 2024 to allow for the admission of an additional 130 nursing students annually, with at least 5% of students being either minority, disabled, or individuals over 60 years old. | GCC | Number of new nursing students enrolled at Germanna, including counts of those who are a minority, disabled, or over 60 years old | 130 students per year with 5% being a minority, disabled, or over 60 years old | Timeline will be delayed given the opening of the Center Street location will not occur until Fall 2024.
|  |  |  | Information on specifically how the program has expanded to allow for the admission of these additional students | n/a | Center Street facilities acquired. Renovations projected to be complete in Fall 2024. As the closing on the Center Street facility was delayed, opening of the facility will not occur until 2024 thereby extending the expansion timeline. The first students to enter the new Stafford Building will occur Fall 2024. Projected dates will need to be modified.
|  | Strategy 2: GCC will hire nine additional full-time nursing faculty, including at least one minority, disabled, or over 60 years old faculty member, by June 30, 2025 to provide didactic and clinical instruction for incoming students. | GCC | Number of full-time nursing faculty hired and count of minority, disabled, or over 60 years old faculty members | 9 by June 30, 2025, with at least one being a minority, disabled, or over 60 years old | Strategy will need to be delayed as faculty will increase as admission of students increases.
|  | Strategy 3: By June 30, 2025, GCC will secure additional clinic sites throughout the region, including rural and underserved areas, to accommodate additional clinicals for students. | GCC | Information about additional clinical sites, including number of sites, location, number of students they can accommodate, and type of organization | n/a | Germanna has attained permission to use some Richmond area facilities. Additionally, two former Long Term Care clinical spaces closed to students due to COVID-19 restrictions have now reopened for clinicals.
|  | Strategy 4: By June 30, 2025, GCC will hire adjunct faculty to provide clinical instruction for nursing students unable to be facilitated by full time faculty. | GCC | Number of adjunct faculty hired | 10 | Increase will occur by 2025 as the student enrollment will increase. Center Street opening was delayed; so need for these faculty will not occur until students are enrolled.
| Objective 5: Support current mental health providers within PD16 and students working towards mental health credentials by March 31, 2025. | Strategy 1: Starting July 1, 2022 and ending March 31, 2025, MHAfred will provide additional support to providers listed in MHAfred’s HELPLINE, including networking opportunities, monthly newsletters, expanding the number of providers offering supervision to students seeking a degree and graduates seeking licensure by 50, and increasing the number of providers using the Unite US platform by 50%. | MHAfred | Information about the specific support MHAfred provided to providers, including the number of providers assisted by specific opportunity | n/a | The first networking session for mental health providers was held on September 16, 2022, and 37 providers attended. The next session will be held on October 21, 2022.
|  |  |  | Number of providers offering supervision of students seeking a degree | 50 | MHAfred is partnering with Youth Life Services (YLS) and Walker Grant Middle School in Fredericksburg City to utilize supervised hours for graduates seeking licenses as clinical social workers for after-school counseling sessions with students identified as being at risk for suicide and having parental consent to receive therapy. Implementation will occur during the spring of 2023.
|  |  |  | Number of providers using the Unite Us platform | 36 | MHAfred's marketing efforts increased the number of mental health providers enrolled in Unite Us by 92%, from 24 providers at the beginning of FY23 to 46 at the end of the first quarter. Additionally, MHAfred met with other stakeholders responsible for increasing usage - MWH, Health Department, and Unite Us - to discuss the next steps now that MHAfred has met its assigned goal of 50%. It was agreed that MHAfred would continue adding out-of-network providers into Unite Us, and Unite Us staff will follow up directly with these leads for recruitment onto the platform.
|  | Strategy 2: Starting July 1, 2022 and ending March 31, 2025, MHAfred will partner with GCC and UMW to offer a minimum of 240 volunteer hours per year to enrolled students needing direct and indirect service hours, including Germanna’s Paraprofessional Counseling Career Studies Certificate program where the volunteer hours will come from working on the HELPLINE and support programs. | MHAfred | Number of volunteer hours per year Germanna Paraprofessional Counseling Career Studies Certificate program students and UMW students obtain through MHAfred, including information about where these hours came from (HELPLINE, support programs, etc.) | 60 hours per quarter | 107
|  |  |  | Number of students working with MHAfred to obtain volunteer hours for the Germanna Paraprofessional Counseling Career Studies Certificate program and UMW | n/a since it depends on availability of work | Among the eight students volunteering at MHAfred, none are from GCC. These students are from UMW and Howard University and have 107 volunteer hours during this first quarter. These students were each onboarded before CHIP deliverables were assigned, and there was no physical space to onboard more students. Discussions are in place to provide GCC volunteer opportunities during the upcoming spring semester.