## schedule
CONSTRUCTION PROJECT SCHEDULE FOR VDH-OFFICE OF DRINKING WATER FINANCIAL AND CONSTUCTION ASSISTANCE PROGRAMS (FCAP)
Project Name: _____________________________________ |  | VDH Project Number:_________________
Prepared By:______________________________________ |  | Prepared Date: ____________________ |  |  | Revised Date(s): _______
| ACTION | Responsible | Start Date |  | Completion Date
|  | Party | Planned | Actual | Planned | Actual
FUNDING APPLICATION & PROJECT MANAGEMENT
1. | Obtain Governing Body approval for project. | Owner
2. | Schedule (by Feb 15th) and attend Preliminary Engineering Conference at VDH-ODW Field Office | Owner
3. | Prepare and submit "Application for Construction Funds" and "Construction Project Schedule | Owner
4. | Designate local contact person responsible for project management;i.e., Recipient's Project Manager. | Owner
5. | Attend Workshop/Initial Meeting with VDH-FCAP staff. | Owner
6. | If extended, accept VDH-FCAP initial offer of project funding terms. | Owner
ENGINEERING
7a. | Prepare Request For Proposal (RFP) for engineering services. | Owner
7b. | Advertise for proposals. (assume 30 days) | Owner
7c. | Evaluate proposals and conduct negotiations. | Owner
7d. | Award contract to top ranked offeror. | Owner
7e. | Submit engineer procurement information to VDH-FCAP Project Officer for approval (if you are requesting reimbursement). | Owner
7f. | Sign contract. | Owner
8 | Submit "Permit Application – Notification of Intent" to VDH Field Office | Owner/Engineer
9a. | Preliminary Engineering Report (PER) -Start Preparation. | Engineer
9b. | Submit PER to (1) VDH-ODW Field Office for approval and (2) forward a copy to VDH-FCAP Project Engineer . (Comments or approval is normally given to applicant by VDH-ODW Field Office within 45 days of receipt. If the VDH-ODW Field Office returns comments, the Project Schedule may need to be adjusted.) | Engineer
9c. | VDH-ODW Field Office approval of PER | VDH-ODW FO
10a. | Prepare Plans and Specifications (P & S). | Engineer
10b. | Submit P & S to (1) VDH-ODW Field Office for approval and (2) forward a copy to VDH-FCAP Project Engineer.(Comments or approval is normally given to applicant byVDH-ODW Field Office within 60 days of receipt. If theVDH-ODW Field Office returns comments, the Project Schedule may need to be adjusted.) [target loan closing 200 days after submit] | Engineer
10c. | VDH-ODW Field Office approval of P & S. allow 60 days | VDH-ODW FO
11. | Review PG #7 and determine type of review applicable for project. Discuss basis with VDH-FCAP Project Engineer. | Owner/Engineer
12a. | If a CE appears to be appropriate, forward a request for a CE to the VDH-FCAP Project Engineer. Include required supporting documentation | Owner/Engineer
12b. | Coordinate the VDH-FCAP Project Engineers' site visit. | Owner/Engineer
12c. | VDH-FCAP Project Engineer sends comments. | VDH-FCAP
12d. | Respond to the VDH-FCAP Project Engineer's comments. | Owner/Engineer
12e. | If VDH-FCAP concurs with a CE, publish the Public Notice provided by VDH-FCAP and allow for a 30 day comment period. Ensure a copy of the completed Public Notice Verification Sheet is provided to VDH-FCAP Project Engineer. Perform procedures in accordance with instructions provided by VDH-FCAP Project Supervisor. | Owner
12f. | If there are no significant adverse comments, the VDH-FCAP Division Director issues letter stating the environmental review requirement has been satisfied. | VDH-FCAP
13a. | If an EA is required, develop EA in accordance with PG #7. | Owner/Engineer
13b. | Forward a written request transmittal to all appropriate review agencies, and allow for a 30 day review and comment period. | Owner/Engineer
13c. | Coordinate the VDH-FCAP Project Engineer's site visit. | Owner/Engineer
13d. | Prepare EA after review agencies’ written responses are received. EA must satisfactorily resolve any review agency comments. | Owner/Engineer
13e. | Publish a Public Notice of public hearing at least 30 days prior to the date of the public hearing in accordance withPG #7. Ensure a copy of the completed Public Notice Verification Sheet is provided to the VDH-FCAP Project Engineer. The public hearing is held after the EA is completed. | Owner
13f. | Provide two copies of the following to VDH-FCAP Project Engineer -Copies of the review request transmittal letters to the review agencies. -Copies of review agency comments. -Response(s), as necessary, to the review agency comments. -A summary or record of the public hearing along with the verification of public notice for the hearing (if not previously provided by the newspaper). -EA or Revised EA (as appropriate). | Owner/Engineer
13g. | If USDA-Rural Development is a funding participant on the project, also send two copies of all items in 13f to them. | Owner/Engineer
13h. | VDH-FCAP Project Engineer sends comments. | VDH-FCAP
13i. | Respond to the VDH FCAP Project Engineer's comments. | Owner/Engineer
13j. | If all comments are satisfactorily addressed, the VDH- FCAP Project Supervisor forwards a copy of the Finding of No Significant Impact (FONSI) Public Notice, a Public Notice Verification Sheet,an example transmittal letter, and instructions. Publish the Public Notice and allow for a 30-day comment period. Ensure a copy of the completed Public Notice Sheet is provided to the VDH-FCAP Project Engineer. | Owner/Engineer
13k. | If no significant adverse comments are received from the public, the VDH-FCAP Division Director issues clearance letter completing the environmental review. | VDH-FCAP
WATERWORKS BUSINESS OPERATIONS PLAN (WBOP)
If required, coordinate process with the VDH-ODW Field Office.
14a. | Prepare WBOP. Allow 120 days for preparation and approval. | Owner
14b. | Submit WBOP to VDH-ODW Field Office for approval. | Owner
14c. | Forward copy of WBOP to VDH-FCAP Project Officer. | Owner
14d. | VDH-ODW Field Office approval of WBOP. | VDH-ODW FO
OTHER REQUIREMENTS
15. | For Parity issues prepare and submit required information to VRA and other lenders 120 days prior to closing. Keep the VDH-FCAP Project Engineer informed of your progress. | Owner
16. | Obtain ownership to any land needed for the construction of the project. Immediately inform the VDH-FCAP Project Engineer of any complications which will delay the project. | Owner
17. | Obtain easements for land needed for construction of theproject. Immediately inform the VDH-FCAP Project Engineer of any complications which will delay the project. | Owner
18. | Obtain funding approval from other lender if project is being co-funded. Forward copy of funding approval or denial to the VDH-FCAP | Owner
19a. | Submit draft Water Users Agreement to VDH-FCAP Project Officer for Approval | Owner
19b. | Submit a signed Water Users Agreement and Certification to VDH-FCAP Project Officer for approval. Forward a copy of Certification to Virginia Resources Authority (VRA). | Owner
20a. | Respond to VRA's request for information needed for their completion of the Credit Summary. | Owner
20b. | VRA completion of Credit Summary. | VRA
21. | VDH State Health Commissioner authorizes final funding terms and issuance of loan commitment letters. | VDH
22a. | VRA forwards Commitment Letter and initial draft of the Financing Agreement and Grant Agreement (if applicable). | VRA
22b. | Execute and return Commitment Letter provided by VRA. | Owner
CONSTRUCTION BID
23a. | Prepare draft Construction Bid documents to include required VDH contract inserts, and bid advertisement. | Engineer
23b. | Submit draft Construction Bid documents and bid advertisement to VDH-FCAP Project Engineer for concurrence prior to bid advertisement. | Engineer
23c. | VDH-FCAP approval of Bid documents. | VDH-FCAP
23d. | Advertise for bids (assume 30 days for advertising) | Owner/Engineer
23e. | Open/Tabulate bids (close loan 60 days after bid opening) | Owner/Engineer
23f. | Inform VDH-FCAP Project Officer and VRA of readiness to proceed with loan closing | Owner/Engineer
23g. | Obtain MBE/WBE solicitation information from selected contractor prior to contract award. | Owner/Engineer
23h. | Forward bid tabulation and other required documents, to include MBE/WBE information, to VDH-FCAP Project Officer for procurement concurrence. | Owner/Engineer
23i. | Inform VDH-FCAP Project Engineer of date and location of Preconstruction Conference at least two weeks prior to meeting. | Owner/Engineer
LOAN CLOSING
24. | Secure the services of a bond counsel to begin the loan closing process 90 days before the project is advertised for receipt of bids. | Owner
25. | Submit Project Budget to VDH-FCAP Project Officer at the initiation of the closing process. | Owner/Engineer
26. | Submit first Request for Disbursement to VDH-FCAP Project Officer two weeks prior to scheduled closing date. | Owner/Engineer
27. | VDH approves loan closing. | VDH
28. | Forward required closing documents to VRA. | Owner
29. | VRA approval of closing documents. | VRA
30. | Set Closing Date - (target is 60 days after bid opening). | VRA/Owner
| CONSTRUCTION | Construction can begin prior to loan closing with VDH approval.
31. | Award construction contract | Owner
32. | Construction start date/Issue Notice to Proceed. | Owner
33. | Construction completion date (from construction contract). | Owner/Engineer
Approved By: _____________________________________ |  |  | Date ______________________
Waterworks’ Project Manager/Owner
Note: The Responsible Party is the person or firm to whom the task is assigned. This schedule includes key steps required to bring a project to Loan Closing. Several steps can be performed concurrently to expedite the overall process. Examples are the Environmental Review and Waterworks Business Operations Plan.
Section 7 of the "Procedural Guidelines (PG) for Virginia Water Supply Revolving Fund Recipients" describes the Required procedures. A Categorical Exclusion (CE) normally takes 60-90 days and an Environmental Assessment (EA) normally takes 90-120 days. An Environmental Impact Statement (EIS) is not included in the steps below as it is rarely required.